## To-do list
Feature Backlog
To be completed by: |  | CSE6360 Team 16
Deadline: |  | April 29th, 2016
Register for the Game/Very High
% done | Type of User | Sprint Release Data | Priority | Hours Spent | Description
100% | User | 2016-04-01 | High | 3 hours | As a user, I want to have my name appear at the left of the start panel.
100% | User | 2016-04-01 | High | 3 hours | As an user, I want to be able to register as a player so my statistics can be recorded.
Play the Game / Very High
% done | Type of User | Sprint Release Date | Prioirity | Hours Spent | Description
100% | User | 2016-04-15 | High | 1 hour | As an user, I want to be able to play the game in order to have fun.
100% | User | 2016-04-15 | High | 3 hours | As an user, I want to be able to roll the die so I can increment my score.
100% | User | 2016-04-15 | High | 3 hours | As an user, I want to be able to see a counter to see my score during the game.
100% | User | 2016-04-15 | High | 3 hours | As an user, I want to be able to pop the balloon so I can reach the objective of the game.
100% | User | 2016-04-29 | High | 3 hour | As an user, I want to be able to play as many games as I want.
100% | User | 2016-04-29 | Medium | 5 hours | As an user, I want to be able to win so I can beat the other players.
100% | User | 2016-04-29 | Low | 1 hour | As an user, I want to be able to lose so it is fair to the other players.
Statistics Info / High
% done | Type of User | Sprint Release Date | Priority | Hours Spent | Description
100% | User | 2016-04-29 | High | 1 hour | As a user, I want to be able to see my statistics so I can see my progress as a player.
100% | User | 2016-04-29 | High | 3 hours | As a user, I want to be able to have my statistics translated into rankings so I can see how I stand among other players.
100% | Administrator | 2016-04-29 | High | 5 hours | As an administrator, I want to be able to update players’ statistics so their latest scores go in the database.
100% | Database | 2016-04-15 | High | 4 hours | As a database, I want to be able to store players’ statistics so they can access their latest progress in the game.
100% | Database | 2016-04-15 | High | 3 hours | As a database, I want to be able to refresh players’ statistics when the administrator makes changes to the statistics.
100% | Database | 2016-04-15 | High | 3 hours | As a database, I want to be able to calculate players’ rankings from their statistics so they can gauge their progress among other players.
100% | User | 2016-04-29 | Medium | 3 hours | As a user, I want to be able to see other players’ statistics so I can compare our progress.
100% | Administrator | 2016-04-29 | Medium | 3 hours | As an administrator, I want to be able to view players’ statistics to handle what goes in the database.